## Release Summary
Release | PI7
Release Month | 2022-10-07
|  | Sl. No. | Release Item | Release | Version | Release type
|  | 1 | Asynchronous functions for c4c patch update | P01-Release-1 |  | New Feature

## Cutover Activities
Sl. No. | Tasks | Owner | Activity type | Duration (in hour) | Start Date | End Date | Comments
Release
1 | C4C Atlas function deployment | Sudheer | pre-cutover |  |  | 2022-07-10
2 | C4C Atlas MongoDB rules deployment | Ateet | pre-cutover |  |  | 2022-07-10
3 | C4C Atlas function configuration deployment | Nagaraj | pre-cutover |  |  | 2022-07-10
4 | PROD Pipeline For APIM Subscription Key | Sayantan | pre-cutover |  |  | 2022-07-10
5 | Spot Check function deployment | Sayantan | post-cutover |  |  | 2022-07-10
6 | Spot Check MongoDB rules & function configuration | Nagaraj | post-cutover |  |  | 2022-07-10
7 | Sanity Test function deployment | Sudheer | post-cutover |  |  | 2022-07-10
8 | Sanity Test MongoDB rules & function configuration | Nagaraj | post-cutover |  |  | 2022-07-10
RollBack
1 | C4C Atlas function deployment | Sudheer | rollback |  |  | 2022-07-10
2 | C4C Atlas MongoDB rules deployment | Ateet | rollback |  |  | 2022-07-10
3 | C4C Atlas function configuration deployment | Nagaraj | rollback |  |  | 2022-07-10
4 | PROD Pipeline For APIM Subscription Key | Sayantan | rollback |  |  | 2022-07-10
5 | Spot Check function deployment | Sayantan | rollback |  |  | 2022-07-10
6 | Spot Check MongoDB rules & function configuration | Nagaraj | rollback |  |  | 2022-07-10
7 | Sanity Test function deployment | Sudheer | rollback |  |  | 2022-07-10
8 | Sanity Test MongoDB rules & function configuration | Nagaraj | rollback |  |  | 2022-07-10