## Refactor the code for POC's
Id | Task | Description | Estimate in hours | Assigned
1 | Analaysis and design the refactor solution. | The design document preparation and decide the actual plan of implementation. | 12 | Sudheer
2 | c4c_xxx_http function creation make code configurable | Create the FAÇADE function which will intake request and insets the request as event. | 8 | Ateet
3 | c4c_xxx_http function implementation to identify the workflow name. | Implement the FAÇADE function which will identify the workflow identifier from request.params and form the eventData from input request and workflow identifier. Use this for .db("sbs-extensions").collection("c4c-ticket-events") for saving the Events | 8 | Ateet
4 | c4c_xxx_http function handle the response and log the neccessay request data. | Log sufficient information to record Request and responses. Ideally the response should be set as status code 201 and Event data saved successfully. | 16 | Ateet
5 | c4c_xxx_update_no_http function creation and make the code configurable and it wil work for any workflow. | Create the function and accept the changedEvent as parameter. Implement the configuration logic | 8 | Ateet
6 | c4c_xxx_update_no_http function make the ruleset configurable in db and able to fetch based on same workflow identifier.. | Make the ruleset configurable in db and able to fetch based on same workflow identifier. | 8 | Nagaraj
7 | c4c_xxx_update_no_http function perform the get operation to pull the ticket record based ticket_id passed. | Perform the get operation to pull the ticket record based ticket_id passed. Make sure if the intended target field is already updated to the required value skip the entire operation. Ensure that function will be able to process any workflow event and complete the patch operation. | 8 | Nagaraj
8 | c4c_xxx_update_no_http function perform the rule execution operation after forming the rule engine request based workflow identifier | Perform the rule execution operation after forming the rule engine request based workflow identifier | 16 | Nagaraj
9 | c4c_xxx_update_no_http perform the patch operation based on the rule exection success status and based on the workflow identifier. | perform the patch operation based on the rule exection success status and based on the workflow identifier. Again make sure if the inetnded field is updated to the required value skip the entire process. | 18 | Nagaraj
10 | c4c_xxx_update_no_http perform function perform the logging for all the required inut/output data with meaningfull messages. | perform the logging for all the required inut/output data with meaningfull messages. | 12 | Ateet
11 | Create the DB trigger c4c_xxx_update_db_trigger and ensure to pass changedEvents to function c4c_xxx_update_no_http | Test the trigger and ensure to pass changedEvents to function c4c_xxx_update_no_http | 6 | Sudheer
13 | Copy all the three rules to c4c-side-by-side.RulesCollection | Move all the 3 POC rules collection into c4c-side-by-side.RulesCollection | 8 | Sudheer
14 | The workflow testing with Testing team | The deep dive expedition of each testcases being prepared by various rule conditions and make sure all cases are working fine | 24 | Sudheer/Nagaraj